## SHMP Action Status Tracker
Goal | Strategy | Action Number | Priority | Actions | Source | Hazard(s) Addressed | Entities | Lead | Final Status | Status Narrative
GOAL: Protect, restore and enhance Vermont’s natural resources to promote healthy, resilient ecosystems. | Promote land management standards for State and private lands | 1 |  | Implement ANR's flood resilience guidelines on ANR Lands. | Aug 2017 WG (1.3.3) | Inundation; Fluvial Erosion | ANR, ANR's State Lands Sub-Committee | ANR - State Lands | Complete | This action was completed through appication of the State's flood hazard river corridor rule as well as by including the basin planners on each of the five District Stewardship Teams in the Long Range Management planning for state lands.
|  | 2 |  | Expand ANR's flood resilience guidelines into a consistent state land management policy to increase and maintain flood storage and attenuation on all state-owned land. | Expert Review (RM #5, 1.3.3) | Inundation; Fluvial Erosion | ANR, BGS | ANR - State Lands | Complete | This action was completed through the No Adverse Impact rule.
|  | 3 |  | Support ongoing efforts to identify strategies for funding and assisting private landowners with essential hazard mitigation and clean water projects. | Dec WG / SHMP 2013 (RM #87) | Inundation; Fluvial Erosion | ANR, VEM, AAFM, VTrans, High Meadows Fund |  | Complete | This action was completed through the Flood Resilient Communities fund and USDA EWP program.
|  | 4 | Yes | Work with land conservation organizations to include river corridor and floodplain protection provisions, and/or headwater storage in conservation easements. | Expert Review | Inundation; Fluvial Erosion | ANR, VHCB, VRC, VLT, NRCD | ANR - Rivers | Complete | This action is complete and ongoing through the FRCF and ongoing collaboration with the Vermont Housing and Conservation Board, the Vermont Land Trust and the Vermont River Conservancy to secure river easements.
| Improve headwater storage | 5 | Yes | Develop an inventory of critical headwater and floodplain storage areas that would result in a measurable abatement of flooding. | WG June 2017 | Inundation; Fluvial Erosion | ANR, USGS, TNC, VLT, UVM, VRC | TNC | Revised / Incorporated | This action is in process and is included in the 2023 SHMP strategy with updated language to reflect progress in new resources and tools available for implementation.
|  | 6 | Yes | Complete a pilot project in a strategic watershed, using the above inventory, to prioritize land conservation and determine the cost of averted flood damage. | Focus Group | Inundation; Fluvial Erosion | ANR, USGS, TNC, VLT, UVM, VRC | TNC | Revised / Incorporated | This action was removed and incorporated into the above action in the 2023 SHMP. This action is also addressed in the Climate Action Plan (CAP) actions related to Vermont Conservation Design priority areas.
|  | 7 |  | Conserve land identified in the critical headwater storage inventory through landowner outreach and existing conservation programs. | WG June 2017 | Inundation; Fluvial Erosion | ANR, Watershed Groups, RPCs, Land Trusts, VRC |  | Revised / Incorporated | This action was revised and incorporated in new mitigation strategies that meet the objective. It is also address in the CAP actin for education and land conservation.
|  | 8 |  | Identify critical headwater storage areas enrolled in the Current Use program and conduct outreach to inform landowners of the value of protecting these areas during harvesting operations. | Focus Group | Inundation; Fluvial Erosion | ANR, AAFM, VRC | AAFM, ANR | Revised / Incorporated | This action was revised incorporated into new mitigation strategies that meet the objective. It is also address in the CAP action for funding technical assistance and outreach to maintain intact forestland parcels.
|  | 9 |  | Identify stormwater-impaired headwater storage areas where stormwater treatment and stream restoration would result in hazard mitigation co-benefits. | Expert Review | Inundation; Fluvial Erosion | ANR, RPCs, VEM, VRC | ANR - Clean Water | Complete | This action is complete through the Vermont stormwater 3-acre rule and Functioning Floodplain Initiative (FFI) tool.
| Reduce negative impacts of in-stream work | 10 |  | Create a working group to explore potential strategies to reduce negative impacts from heavy equipment operators who work in rivers (i.e., tailored Rivers and Roads Training Tier 3). | Expert Review / SHMP 2013 (3.4.1) | Inundation; Fluvial Erosion | ANR, VTrans, VEM, TNC, RPCs | ANR - Rivers | Complete | This action was completed through the development and implementation of Tier 3 Rivers and Roads Training courses.
|  | 11 |  | Develop a rapid-response field task force (river engineers, scientists, restoration specialists, transportation engineers and RPC staff) to provide regulatory, technical and administrative assistance for in-stream reconstruction projects and mitigation measures in the immediate aftermath of major flood disasters. | SHMP 2013 Priority (3.3.1) | Inundation; Fluvial Erosion | ANR, RPCs, VTrans, VEM | ANR - Rivers | Complete | This action objective was completed through a Web platform developed by River Engineers for stream alteration permits after disaster.
|  | 12 |  | Institute an effective outreach and training program to assist municipalities in complying with Vermont's new rules for conducting instream emergency protective measures. | Expert Review / SHMP 2013 3.1.4 | Inundation; Fluvial Erosion | ANR, RPCs, VTrans, VEM | ANR - Rivers | Complete | This action was completed through website resources on in-stream emergency protective measures and information included in training and outreach initiatives.
|  | 13 |  | Incorporate ANR's Standard River Management Principles and Practices into in the VTrans Orange Book to ensure municipalities adopt the same standards. | SHMP 2013 (RM #5) | Inundation; Fluvial Erosion | ANR, VTrans | VTrans | Complete | This action was completed through the updates to the Orange Book and the Municipal Roads General Permit (MRGP).
| Improve flood resilience of agricultural lands | 14 | Yes | Create a working group to develop a coordinated assistance strategy (funding mechanisms, technical support, directory of available resources) to further improve the resilience of agricultural lands and their contribution to flood resilience. | SHMP 2013 (RM #31, #33, #88) | All Hazards | AAFM, ANR, UVM Extension, NRCS, VLT, High Meadows, NRCDs, VRC, NRCD | AAFM | Complete | This action is complete through Implementation through the Agriculture and Ecosystems subcommittee for the CAP, and incorporation of resources in the Climate Toolkit.
|  | 15 |  | Expand use of USDA conservation programs to plant riparian buffers and flood chute grassed waterways to reduce future flood damage to farm fields, attenuate flood-borne sediment and debris, and reduce downstream flooding. | Expert Review / SHMP 2013 (3.2.6) | Inundation; Fluvial Erosion | AAFM, USDA, UVM Extension | AAFM | Revised / Incorporated | This action was incorporated into a new action in the 2023 SHMP and also addressed by CAP actions on agriculture. Progress was made through the Grassed Waterway and Filter Strip (GWFS) Program.
| Promote drought resilience | 16 |  | Expand the number of monitoring wells (in both bedrock and surficial materials) to include drilled wells which will provide data for tracking water level and responses to precipitation. | Expert Review | Inundation; Fluvial Erosion; Drought | ANR, USGS | ANR - State Geologist, USGS | Revised / Incorporated | This action is in progress and was moved to the 2023 SHMP mitigation strategy. USGS now has 3 real-time monitoring wells in Rutland, Windsor and Orleans counties.
|  | 17 |  | Analyze water level/monitoring data to use as predictor of drought and rates of recovery. | Expert Review | Drought | ANR, USGS | ANR - State Geologist, Drought Task Force | Revised / Incorporated | This action was moved to the 2023 SHMP mitigation strategy and incorporated into an action for Drought Plan.
|  | 18 |  | Develop statewide groundwater resource maps, water use and water level data in order to determine water budgets for local areas in preparation for drought conditions. | SHMP 2013 (5.1.10) | Drought | ANR | ANR - State Geologist | Revised / Incorporated | This action was moved to the 2023 SHMP mitigation strategy.
| Connect water quality, flood resilience and native habitat connectivity through co-benefits | 19 | Yes | Create a “Reconnect Vermont Rivers” initiative (or similar state planning, prioritization, and tracking mechanism) to enhance the funding eligibility and incentives for flood resilience, water quality, and habitat projects as co-benefits. | Expert Review | Inundation; Fluvial Erosion | ANR, TNC, AAFM, WUV, VTrans, VLT, VRC, NRCD | ANR - Rivers | Complete | This action is completed through the FFI.
|  | 20 | Yes | Develop hydraulic and stream power models for a range of flood frequencies to analyze and define valley areas supporting essential floodplains and river corridor functions that would increase the storage of flood flows, sediments, and nutrients. | Expert Review | Inundation; Fluvial Erosion | ANR, UVM, TNC, VLT, USGS, NRCD | ANR - Rivers | Complete | This action is completed through the FFI.
|  | 21 |  | Promote the use of Vermont Fish and Wildlife's Conservation Design Plan to achieve and maintain habitat connectivity and havens for Vermont rare, threatened, and endangered species (aquatic and terrestrial). | Expert Review | Invasive Species; Inundation; Fluvial Erosion | TNC, ANR, VHCB, NRCS, Land Trusts, VLCT, RPCs | ANR - Rivers | Incomplete / Removed | This action was removed as it was deemed to not be hazard mitigation.
GOAL: Enhance the resilience of our built environment - our communities, infrastructure, buildings, and cultural assets. | Locate new development outside of hazardous areas | 22 |  | Secure funding to create a permanent all-hazard mapping position at ANR (as created by SHMP 2018 subgrant). | Expert Review / SHMP 2013 (RM #75) | All Hazards | ANR, VEM | ANR - Rivers | Complete | This action is complete and mapping person is onboarded.
|  | 23 | Yes | Develop a mechanism for tracking new structural development in the river corridor so development patterns can be tracked over time. | WG June 2017 | Inundation; Fluvial Erosion | ANR, UVM, VCGI, RPCs | ANR - Rivers | Incomplete / Removed | This action is captured by Vermont river corridor regulations.
|  | 24 | Yes | Research reasonable steps developers can take to site new structural development outside of hazard-prone areas when the State is involved in funding, consistent with State river corridor standards and land use goals. | Dec WG / SHMP 2013 Priority (1.2.1, New 4.2) | Inundation; Fluvial Erosion; Landslide | ANR, AOA, VEM, VTrans |  | Revised / Incorporated | This action objective is addressed through multiple actions in the 2023 SHMP actions in the land use management category.
| Develop resilient design and construction standards | 25 | Yes | Develop sample building standards for resilient design and construction (for buildings, construction sites, transportation infrastructure, etc.). | Expert Review | All Hazards | ANR, VTrans, RPCs, Norwich | Norwich | Revised / Incorporated | This action was incorporated into 2023 SHMP actions to develop resilient design and construction standards.
|  | 26 |  | Audit existing building codes to ensure that standards account for anticipated climate change impacts to Vermont, including but not limited to increased temperatures extremes and precipitation. | Expert Review | All Hazards | Norwich, DPS - Fire Safety | Norwich | Revised / Incorporated | This action was incorporated into 2023 SHMP actions to develop resilient design and construction standards. This action was also included in the CAP.
|  | 27 |  | Create educational resources for contractors, municipalities and property owners on resilient design and construction techniques. | Dec WG | All Hazards | Norwich, VTrans, DPS (Partner with Efficiency VT) | Norwich | Incomplete / Removed | This action was removed and is covered by actions in the 2023 SHMP and CAP on weatherization.
|  | 28 | Yes | Research how applicants can demonstrate they have taken reasonable steps to incorporate resilient design and construction in hazard-prone areas when the State is involved in funding, consistent with the objectives of the funding source. | Expert Review | All Hazards | All State Agencies, RPCs | Project Review Committee | Revised / Incorporated | This action objective is incorporated into a new action for transporation system resilience.
| Incorporate flood resilience in transportation planning, engineering and programming | 29 | Yes | Secure funding to expand the VTrans Methods and Tool for Transportation Resilience application (as developed by the 2018 SHMP subgrant) to all watersheds in the State. | Aug 2017 WG | Inundation; Fluvial Erosion | VTrans, VEM, RPCs | VTrans | Complete | This action was completed with the Transporation Resilience Planning Tool (TRPT) covering 100% of the state and available to the public.
|  | 30 |  | Incorporate metrics for flood resilience into the VTrans project prioritization process. | Aug 2017 WG | Inundation; Fluvial Erosion | VTrans, ANR, VEM | VTrans | Complete | This action is complete. The flood resilience metric is included in the VTrans Project Selection and Prioritizations Process (VPSP2).
|  | 31 |  | Incorporate river and road resilience principles and practices developed by ANR and VTrans (through 2018 SHMP subgrants) into municipal technical assistance and funding to encourage local road maintenance and upgrades that reduce flood-related vulnerabilities. | Expert Review | Inundation; Fluvial Erosion | VTrans, ANR, VEM, RPCs | VTrans, ANR-Rivers | Complete | This action is complete through ongoing technical assistance and funding mechanisms.
|  | 32 |  | Identify, evaluate and implement design standards and operational practices for state transportation infrastructure necessary to accommodate extreme weather conditions. | SHMP 2013 (4.1.1, RM #17) | All Hazards | VTrans, Norwich, RPCs | VTrans | Revised / Incorporated | This action was in part completed through the update to the VTrans hyrdraulic manual and incorporation of resilient standards for sizing of culverts and bridges. It was also incorporated into 2023 actions for transporation resilience and the CAP.
| Assess seismic vulnerability | 33 |  | Conduct thorough seismic analyses of select bridge sites, based on UVM's seismic vulnerability ranking system, and prioritize projects. | SHMP 2013 (5.1.13) | Earthquake; Landslides | VTrans, ANR, UVM Transportation Research Center | ANR - State Geologist | Revised / Incorporated | This action was included in the 2023 SHMP for further analysis and project prioritization. Vtrans and the FHA funded a study published in 2019 to look at sesmic vulnerability of bridges in Vermont.
|  | 34 |  | Conduct detailed seismic analyses for critical facilities identified in the 2016 NESEC study as well as cultural facilities using HAZUS and ROVER. | SHMP 2013 (3.1.9, 5.1.11) | Earthquake; Landslides | ANR, NESEC, VEM, BGS, SHPO | ANR - State Geologist | Revised / Incorporated | This action was included in the 2023 SHMP, no work was completed due to lack of funding.
| Identify and protect vulnerable structures and critical infrastructure | 35 |  | Adapt the flood vulnerability methods developed by VTrans Methods and Tool for Transportation Resilience project (2018 SHMP subgrant) and the Vermont Economic Resiliency Initiative (ACCD) for use in identifying other structures, utilities, key employment areas, and critical infrastructure that are vulnerable to damage from floods. | SHMP 2013 (3.2.1) | Inundation; Fluvial Erosion | ANR, VTrans, VEM, ACCD, GMP | VTrans | Incomplete / Removed | The objective of this action was incorporated into new 2023 SHMP actions.
|  | 36 |  | Secure funding to implement the priority mitigation actions list developed by Buildings and General Services (BGS) (2018 SHMP subgrant). | Aug 2017 WG / SHMP 2013 (3.2.1) | Inundation; Fluvial Erosion | BGS, All Agencies | BGS | Revised / Incorporated | This action was included in the 2023 SHMP, no work completed is documented.
|  | 37 |  | Provide technical assistance to utilities in long-range planning for transmission and distribution line upgrades and relocation to improve resilience. | Expert Review | Wind; Ice; Snow | PSD, ANR | PSD | Complete | This action is complete. Utilities files Integrated Resource Plans (IRPs) every three years. PSD provides technical assistance on these IRPs in advance of filing. IRPs include line upgrades and and relocation of substations in the floodplain.
|  | 38 |  | Assist Vermont Gas in evaluating the flood and seismic vulnerability of Vermont’s natural gas pipeline network through the Integrity Management Program, and identify actions to mitigate this risk. | SHMP 2013 (4.7.1) | Inundation; Fluvial Erosion; Earthquake; Landslide | PSD | PSD | Complete | This action is complete. PSD works with VGS to identify and mitigate risks through the Transmission Integrity Management Program (TIMP) inspection.
|  | 39 |  | Require consideration of river corridors in the State permitting process for water and wastewater facility siting or improvement. | SHMP 2013 (1.1.1) | Inundation; Fluvial Erosion | ANR | ANR - Rivers | Complete | This action is complete through the new wastewater siting rule.
|  | 40 |  | Provide technical assistance to municipalities to assess the flood and erosion risks facing their drinking water and waste water systems and identify potential mitigation improvements. | SHMP 2013 (2.1.3) | Inundation; Fluvial Erosion | ANR, RPCs | ANR - Rivers | Complete | This action is complete, assistance is ongoing and provided as needed.
|  | 41 |  | Create a process for relocating or retrofitting at-risk mobile home parks at the time of sale or substantial rehabilitation using the DHCD’s risk assessment tool. | Expert Review / SHMP 2013 (RM #104) | Inundation; Fluvial Erosion; Landslide | ACCD, CVOEO, Housing Foundation | ACCD | Revised / Incorporated | This action was revised and included in the 2023 SHMP.
| Reduce structural vulnerability to landslide hazards | 42 |  | Provide technical assistance to local planners with using the Protocol for Identification of Areas Sensitive to Landslide Hazards to prioritize landslide projects based on risk and develop mitigation options. | SHMP 2013 (3.2.2, 5.1.7) | Landslide | ANR, RPCs | ANR - State Geologist | Revised / Incorporated | This action is in progress and included in the 2023 SHMP. Earthquake hazard communication plans for Chittenden County and the State of Vermont were delivered to the National Earthquake Hazard Reduction Program (NEHRP). NEHRP funding is no longer available. Landslide protocol re-evaluation is on hold because of funding.
|  | 43 |  | Expand landslide hazard mapping to statewide coverage. | Focus Group | Landslide | ANR, VEM | ANR - State Geologist | Revised / Incorporated | This action is in progress and is included in the 2023 SHMP. Several counties have completed landslide inventories with the landslide reporting and mapping tool.
|  | 44 |  | Educate towns and citizens on reporting observed landslides (rockfalls, debris flows, other mass failures) via the landslide hazard online reporting form. | Expert Review | Landslide | ANR, RPCs | ANR - State Geologist | Revised / Incorporated | This action is in progress and is included in the 2023 SHMP. Several landslides have been reported to the landslide reporting and mapping tool.
| Protect cultural and historic resources | 45 |  | Update inventories and mapping of cultural and historic resources located in hazard-prone areas (currently underway at the state level and regionally through FEMA). | Aug 2017 WG / Dec WG | Inundation; Fluvial Erosion | ACCD, VT Arts Council, RPCs, FEMA | ACCD - Historic Preservation | Revised / Incorporated | This action is in progress and revised for inclusion in the 2023 SHMP.The State Register historic districts are mapped. FEMA is no longer mapping National Register districts and Vermont needs funding to complete work. Cultural Resources are being mapped as part of VACDaRN.
|  | 46 |  | Use the updated cultural and historic resources inventory to identify and secure funding for priority cultural and historic structures that can be relocated out of hazardous locations or flood-proofed. | Aug 2017 WG | Inundation; Fluvial Erosion | ACCD, BGS, Arts Council, VHS | ACCD - Historic Preservation | Revised / Incorporated | This action was moved to the 2023 SHMP mitigation strategy. Work is considered ongoing.
|  | 47 |  | Develop and share best practice guides and tool kits for proactive efforts to protect historic buildings, villages and downtowns in floodplains. | June 2017 WG meeting | Inundation; Fluvial Erosion | ACCD, BGS, VT Arts Council, VHS | ACCD - Historic Preservation | Revised / Incorporated | This action was moved to the 2023 SHMP mitigation strategy. Work is considered ongoing. Guidelines on Flood Adaptation for Rehabilitating Historic Buildings, document completed and shared; https://www.nps.gov/orgs/1739/upload/flood-adaptation-guidelines-2021.pdf Future work will be to expand partnerships to RPCs and League of Cities and Towns.
|  | 48 | Yes | Improve communications between mitigation project work and historic preservation review to allow for more rapid approval of shovel-ready projects. | Dec WG | All Hazards | SHPO, VEM, ANR, VTrans, FEMA | ACCD - Historic Preservation, VEM | Complete | This action is complete. VEM, SHPO, and FEMA coordinated revisions the Programmatic Agreement to streamline emergency reviews, particularly in relation to home buyouts.
| Establish a statewide conservation and buyout program | 49 | Yes | Establish a working group to design a robust cross-sector buyout program, considering funding, ownership, use restrictions, incentives, stewardship, prioritization. | SHMP 2013 Priority (RM #91) | Inundation; Fluvial Erosion; Landslide | VEM, ANR, VLCT, VRC, VHCB, ACCD, CLF | VEM | Complete | This action is complete through the FRCF. Sustainable funding is needed to continue program after ARPA funding is no longer available.
|  | 50 |  | Create a dedicated State fund to support the purchase or local match of hazard-prone properties and the purchase of easements to conserve river corridors, floodplains, and wetlands identified as key flood attenuation areas. | Dec WG | Inundation; Fluvial Erosion; Landslide | EWP, ACCD, ANR, FHWA, VHCB, FEMA, USDA, NRCS | VEM | Complete | This action is complete through the FRCF. Sustainable funding is needed to continue program after ARPA funding is no longer available.
|  | 51 |  | Expand the eligibility criteria and increase funding for VHCB's conservation and buyout program, to address any flood-vulnerable structures. | Dec WG | Inundation; Fluvial Erosion | ANR, VHCB, AOA | VEM | Incomplete / Removed | This action is incomplete and removed due to shifting partner priorities.
|  | 52 |  | Fund ERAF for non-federal disasters in towns that have adopted floodplain and/or river corridor bylaws and to support the 25% non-federal match for buyouts and develop criteria for distribution when funding is limited. | Aug 2017 WG | Inundation; Fluvial Erosion | ANR, VEM, AOA | VEM | Revised / Incorporated | This action is revised and included in the 2023 SHMP mitigation strategy.
|  | 53 |  | Create and maintain a database of tax-sale/foreclosed properties located within SFHA and State River Corridor maps to identify flood-vulnerable structures for removal. | 2017 EPC | Inundation; Fluvial Erosion | ANR, VEM, VT Realtors | VEM | Revised / Incorporated | This action is revised and included in the 2023 SHMP mitigation strategy. No progress was made. The action is included in the CAP.
|  | 54 |  | Develop a priority list and map of community-identified properties that have been damaged repetitively but are not on the FEMA Repetitive Loss (RL) or Severe Repetitive Loss (SRL) list to be used for buyout/conservation prioritization. | SHMP 2013 (New 5.1) | Inundation; Fluvial Erosion; Landslide | VEM, ANR, RPCs | VEM | Revised / Incorporated | This action is revised and included in the 2023 SHMP mitigation strategy. No progress was made. The action is included in the CAP.
|  | 55 |  | Develop a Benefit/Cost Analysis methodology to facilitate buyouts in areas at risk from flood-related erosion and outside of FEMA-mapped Special Flood Hazard Areas. | Expert Review (5.1.9) | Fluvial Erosion | VT Silver Jackets, VEM, ANR | VEM | Revised / Incorporated | This action is revised and included in the 2023 SHMP mitigation strategy. Project was considered for technical assistance through Silver Jackets. The action is included in the CAP.
| Improve dam resilience | 56 |  | Conduct and/or update dam breach analyses on significant and high-hazard dams. | 2017 EPC | Inundation; Fluvial Erosion | ANR, VEM | ANR - Dam Safety | Revised / Incorporated | This action is in progress, revised and included in the 2023 SHMP. A dam reclassication review was completed. The VT Dam Safety is utilizing DSS-Wise Lite to develop dam breach flood inundation maps for some signficant and low hazard dams. USACE/Silver Jackets will assist with addtional assessments. New dam safety rules are recently in effect.
|  | 57 |  | Develop rules around requiring Emergency Action Plans (EAPs) to be developed and updated annually or every other year (dam safety bill passed in 2018, Act 162). | Expert Review | Inundation; Fluvial Erosion | ANR, VEM | ANR - Dam Safety | Revised / Incorporated | This action is included in the 2023 SHMP. New rules applicable to EAPs are developed and scheduled for adoption in July 2024.
|  | 58 |  | Complete development and digitize all dam inundation maps for all high hazard dams and perform tabletop exercises for new Emergency Action Plans (EAPs), once generated. | Expert Review / SHMP 2013 (5.1.2) | Inundation; Fluvial Erosion | ANR, VEM | ANR - Dam Safety | Revised / Incorporated | This action is in progress, it was revised and included in the 2023 SHMP.
|  | 59 |  | Develop a new Vermont Dam Inventory to better link data and digital inundation mapping, including more robust contact information for owners, ecological information and Emergency Action Plans (EAPs). | Expert Review | Inundation; Fluvial Erosion | ANR, VEM | ANR - Dam Safety | Complete | This action is complete. A current Vermont Dam Inventory has been transferred to VEM Homeland Security. A new dam mapper is available to the public.
|  | 60 |  | Develop guidance documents/criteria for the security improvement of high hazard dams throughout Vermont. | Expert Review | Inundation; Fluvial Erosion | ANR, VEM, DPS | ANR - Dam Safety | Incomplete / Removed | This action is removed and covered by existing resources.
|  | 61 | Yes | Utilize updated Dam Inventory to support the expansion of the Dam Removal Screening Tool beyond Champlain Basin. | Expert Review | Inundation; Fluvial Erosion | ANR, VEM, TNC, VNRC, Dam Task Force | TNC | Incomplete / Removed | This action is removed due to changed priorities. It is covered by a new action adopted from the CAP.
GOAL: Develop and implement plans and policies that create resilient natural systems, built environments and communities. | Ensure state programs support hazard mitigation goals | 62 | Yes | Audit all state/federal funding/technical assistance programs to determine the degree to which they directly or indirectly help or hinder the ability of the State to achieve Vermont’s State Hazard Mitigation Plan goals. | SHMP 2013 Priority (1.2.1, RM #3) | All Hazards | AOA, ANR, VEM, ACCD, AAFM, CLF | ANR - Rivers, VEM | Revised / Incorporated | This action ws revised and included in the 2023 SHMP. No progress was made.
|  | 63 |  | Following the audit above, develop a set of planning principles and recommendations as a means to align State programs. | Focus Group | All Hazards | ACCD, ANR, VEM | ANR - Rivers, VEM | Revised / Incorporated | This action ws revised and included in the 2023 SHMP. No progress was made.
| Improve incentives for local hazard mitigation planning and action | 64 | Yes | Convene a working group of state agencies, academic partners, regional and local stakeholders to review the effectiveness of existing Emergency Relief & Assistance Fund (ERAF) criteria and river corridor bylaws. | Dec WG / SHMP 2013 (RM #43) | Inundation; Fluvial Erosion | VEM, ANR, VTrans, UVM, RPCs | VEM | Complete | This action is considered complete. Stakeholder outreach results indicated that the program should not be changed, but better State assistance is needed.
|  | 65 |  | Revise the Emergency Relief & Assistance Fund (ERAF) criteria to more effectively incentivize communities to improve their flood resilience. | Dec WG | Inundation; Fluvial Erosion | VEM, ANR, VTrans, AOA | VEM | Incomplete / Removed | This action is removed. Stakeholder outreach results indicated that the program should not be changed, but better State assistance is needed. A new action for this work in included in the 2023 SHMP mitigation strategy.
| Improve local hazard mitigation planning | 66 |  | Create a working group to assess statutory updates to the municipal planning requirements to better coordinate municipal plans and local hazard mitigation plans. | Focus Group | All Hazards | VEM, ACCD, RPCs | VEM, ACCD | Incomplete / Removed | This action was removed and related actions were revised to meet the objective. No progress was made.
|  | 67 |  | Develop a model of an integrated municipal plan and local hazard mitigation plan that meets the requirements of both planning processes. | Dec WG | All Hazards | VEM, ACCD, RPCs | VEM, ACCD | Revised / Incorporated | This action was revised and included in the 2023 SHMP. No progress was made.
|  | 68 |  | Create intuitive Local Hazard Mitigation Plan templates (single and multi-jurisdictional) and development resources, including local engagement tools. | 2017 EPC, Dec WG | All Hazards | VEM, RPCs | VEM | Revised / Incorporated | This work is in progress and the action is revised andincluded in the 2023 SHMP. A template LHMP is in development, and several new resources are available on the Hazard Mitigation Planning Resources webpage. A Climate Toolkit is also under development by the CAO with VEM support.
|  | 69 |  | Develop a Vermont-based potential mitigation actions list for Local Hazard Mitigation Plans from the findings of the ANR subgrant. | 2017 EPC | All Hazards | VEM, ANR, VTrans | VEM | Revised / Incorporated | This work is in progress and the action is revised andincluded in the 2023 SHMP.
|  | 70 |  | Host annual or biannual Local Hazard Mitigation Planning workshops and skill-shares. | Expert Review | All Hazards | VEM, FEMA | VEM | Complete | This action is complete and ongoing through workshops and trainings hosted as needed and on an annual basis by VEM and FEMA.
|  | 71 |  | Request approval from FEMA to participate in Program Admin by State to expedite Local Hazard Mitigation Plan (LHMP) approvals. | VEM | All Hazards | VEM | VEM | Complete | This action is completed. Vermont and FEMA entered an agreement for Program Administration by State (PAS) in 2020. A new action is included in the 2023 SHMP.
|  | 72 |  | Support RPCs in implementing municipal hazard mitigation project tables developed through the ANR subgrant (bake into annual work plans from ANR and VEM funding). | Focus Group | Inundation; Fluvial Erosion | ANR, RPCs | ANR - Rivers | Complete | This action is complete. ANR provides feedback to RPCs as requested.
| Develop solutions to fund hazard mitigation | 73 |  | Host practical, biannual workshop sessions to help applicants prepare Hazard Mitigation Assistance (HMA) grant applications, including sessions on application development, e-Grants, benefit-cost analysis, engineering design and environmental permitting. | SHMP 2013 (2.2.1, RM#21) | All Hazards | VEM, FEMA | VEM | Complete | This action is complete and ongoing. Trainings are held as needed.
|  | 74 | Yes | Convene State, federal and private funders annually to identify ways to better leverage existing funding, fill funding gaps, increase funder alignment, and strengthen funding criteria that relate to hazard mitigation and climate adaptation. | Focus Group | All Hazards | VEM, ANR, VTrans, USDA RD, High Meadows, VHCB, Resilient VT, FHWA, FEMA | VEM, Norwich | Revised / Incorporated | This action is included in the 2023 SHMP. No progress was made.
|  | 75 |  | Develop a clearinghouse directory of mitigation funding opportunities including details on requirements, deadlines, and timeframes that can be available at the local level to implement mitigation action. | Aug 2017 WG | All Hazards | VEM, ANR, VTrans, ACCD, TNC | VEM | Revised / Incorporated | This action is revised/incorporated with CAO led actions for the Climate Toolkit.
|  | 76 |  | Implement the Hazard Mitigation Assistance (HMA) requirements of an Enhanced Plan for the 2023 State Hazard Mitigation Plan update in order to increase HMGP share following a disaster. | VEM | All Hazards | VEM | VEM | Revised / Incorporated | This action is moved to the 2023 SHMP. Capacity building is underway.
GOAL: Create a common understanding of - and coordinated approach to - mitigation planning and action. | Improve local leaders' understanding of hazard mitigation | 77 |  | Complete loss-avoidance studies to better understand the positive impact of completed mitigation work, including the value of open space, forested and conserved land. | Focus Groups | All Hazards | VEM, ANR, VTrans, FEMA, TNC, VRC, UVM | VEM | Revised / Incorporated | This action was revised and incorporated into the 2023 SHMP. A pilot assessment was completed by USACE through Silver Jackets.
|  | 78 | Yes | Develop case studies to showcase replicable pilot projects that reduce community vulnerability. | June 2017 WG meeting | All Hazards | UVM, Norwich | VEM | Revised / Incorporated | This action was revised to focus on frontline communities in the 2023 SHMP. Case studies have been added to the VEM website.
|  | 79 | Yes | Develop strategic capital budgeting training and materials to incorporate mitigation and water quality projects, explain the cost of no action and include municipal liability concerns. | 2017 EPC | Inundation, Fluvial Erosion, Landslide | VEM, ACCD, ANR, VTrans, TNC, VHCB, VNRC, VRC, RPCs |  | Revised / Incorporated | This action was revised and included in the 2023 SHMP. No progress was made.
|  | 80 |  | Promote and maintain technical support to communities to adopt river corridor bylaws, limit development in floodplains and river corridors, and participate in the Community Rating System (CRS). | SHMP 2013 Priority (RM, New 4.2) | Inundation, Fluvial Erosion | ANR, ACCD, RPCs, VLCT | ANR - Rivers | Complete | This action is complete and ongoing.
|  | 81 |  | Integrate hazard awareness and disaster resilience education with existing training opportunities throughout the State. | Aug 2017 WG | All Hazards | VEM, ANR, VTrans, AHS |  | Revised / Incorporated | This action was revised and included in the 2023 SHMP. Work is in progress.
| Increase public knowledge and literacy of hazards and mitigation | 82 |  | Develop an inventory of existing public outreach materials (hazard mitigation opportunities, steps to take following a disaster, etc.), compile or create effective aids and develop a distribution strategy. | Focus Groups | All Hazards | VEM, VDH, ANR, CVOEO, Watersheds United, RPCs | VEM | Incomplete / Removed | This action is being removed beause it is covered by other actions in the 2023 SHMP and CAP.
|  | 83 | Yes | Develop educational materials and dissemination strategy to increase public literacy regarding river science, floodplain function and benefits. | SHMP 2013 (RM #96) | Inundation, Fluvial Erosion | VEM, ANR, State Floodplain Manager, Norwich, Watersheds United, NRCD | ANR - Rivers | Complete | This action is achieved through multiple projects including the FFI and new training on the FloodReady website.
|  | 84 |  | Support education of the general public around invasive species and their role in altering the beneficial functions of natural ecosystems. | WG June 2017 | Invasive Species | ANR, AAFM, TNC | TNC | Revised / Incorporated | This action was revised and included in the 2023 SHMP.
| Improve community resilience and local engagement | 85 |  | Develop educational resources to assist local entities and Regional Planning Commissions in creating and maintaining Community Organizations Active in Disaster (COADs). | Dec WG / SHMP 2013 (NEW 3.1) | All Hazards | AHS, RPCs, CROs, COADs | AHS | Revised / Incorporated | This action was revised and included in the 2023 SHMP. Coordination work is underway with AHS, AAFM, AOE and others.
|  | 86 |  | Support the coordination and capacity of community resilience initiatives at the local level (such as Community Resilience Organizations) to reduce community and individual vulnerability to natural hazards. | Aug 2017 WG / SHMP 2013 (NEW 3.1) | All Hazards | AHS, Norwich, Watershed United, RPCs, CROs | AHS | Revised / Incorporated | This action was revised and included in the 2023 SHMP. Coordination work is underway with AHS, AAFM, AOE and others.
| Strengthen networks that support the resilience of vulnerable populations | 87 |  | Develop guidance and technical support for municipalities to identify and map populations that are potentially vulnerable to hazards. | June 2017 WG meeting | All Hazards | VDH, AHS, RPCs, VCGI |  | Revised / Incorporated | This action is covered by the CAO-led Municipal Vulnerability Index (MVI) work underway and included in the 2023 SHMP and CAP.
|  | 88 | Yes | Gather and disseminate vulnerable population data and analysis for incorporation into municipal and regional plans so that the needs of Vermont’s vulnerable populations are clearly identified and represented. | SHMP 2013 Priority (RM #77) | All Hazards | VDH, VEM, AHS, ACCD, RPCs, CVOEO, VCGI |  | Revised / Incorporated | There are multiple mapping projects to identify environmental justice communities and vulnerability in the State of Vermont. The action is revised and included in the SHMP 2023 and CAP.
|  | 89 |  | Develop statewide database of rental properties using the mobile home database as a model. | Dec WG | All Hazards | CVOEO, DPS, ACCD, Housing Foundation |  | Revised / Incorporated | This action is included in the 2023 SHMP. No progress was made.
|  | 90 |  | Support development of coordinated care network to provide consistent messaging on steps individuals can take to prepare for and reduce vulnerability to natural hazards. | Dec WG | All Hazards | AHS, CVOEO, VAHHS | AHS | Revised / Incorporated | This action is included in the 2023 SHMP. Work is underway. AHS worked with 211 on CARE, the voluntary registry system for individuals to sign up for first responders to be notified of households with unique needs (life support equipment dependent on electricity). The VT Dept of Health translated several documents into multiple languages to address infectious disease/pandemic testing and vaccination efforts. AHS partnered with organizations that focus on providing support to non-English speaking Vermonters.
|  | 91 |  | Support and strengthen the Disaster Case Management (DCM) Network to train case managers working with disaster-affected individuals to aid in their recovery and identify mitigation opportunities. | SHMP 2013 (RM #42) | All Hazards | AHS, VEM, VOAD, COADs, Red Cross | AHS | Revised / Incorporated | This action is included in the 2023 SHMP. Work in in progress. The Individual and Family Needs Recovery Task Force Plan was completed ,including a Multi Agency Resource Annex. AHS conducted Disaster Case Management training in June 2020.
| Coordinate hazard mitigation mapping, data and research | 92 |  | Create inventory of available data across state government, universities and organizations to align conflicting information and identify gaps. | Dec WG | All Hazards | ANR, VEM, VTrans, ADS, ACCD, VCGI |  | Revised / Incorporated | This action is covered by the CAO-led Municipal Vulnerability Index (MVI) work underway and included in the 2023 SHMP and CAP.
|  | 93 | Yes | Coordinate State programs to promote development, sharing and maintenance of hazard-related data and mapping across a common platform. | Dec WG/ SHMP 2013 (5.1.4) | All Hazards | ANR, VEM, VTrans, ADS, ACCD, VCGI, ArmyCorps, NRCD |  | Revised / Incorporated | This action objective was incoporated into other SHMP 2023 actions. Work is in progress through the CAO and Enterprise GIS Consortium.
|  | 94 | Yes | Develop a common and consistent statewide platform for collecting local and regional response and recovery data. | Expert Review | All Hazards | ANR, VEM, VTrans, ADS, ACCD, RPCs | VEM | Revised / Incorporated | This action is included in the 2023 SHMP. Progress on this action included the Reduce Repeat Damages took from VTrans.
|  | 95 | Yes | Support the development of an Academic Resilience Collaborative (ARC) of state agencies, academic partners, researchers, students and entities with research needs around hazard mitigation and resilience. | Dec WG | All Hazards | Norwich, VEM, ANR, VTrans, High Meadows, RPCs | Norwich, VEM | Complete | This action was completed through the Academic Resilience Collaborative (ARC) and Resilient Vermont Network.
|  | 96 |  | Host regular meetings to identify and discuss priority research and project needs for SHMP implementation. | Dec WG | All Hazards | Norwich, VEM, High Meadows, ARC, Resilient VT | Norwich, VEM | Revised / Incorporated | This action was revised and included in the 2023 SHMP mitigation strategy under coordinate hazard mitigation mapping, data and research.

## Sheet1
red column list
Complete | Complete
In Process | Incomplete / Removed
Revisions Needed | Revised / Incorporated
Remove